## Slide 1: Balerica Inc. Cloud Migration Strategy
Phased Approach to AWS Migration
Presented by: Lead Consultant

## Slide 2: Executive Summary
AWS chosen as the primary cloud provider
Strong regional presence (São Paulo + global)
Strategy: 4 phases → Assessment, Migration, Optimization, Ongoing Ops
Timeline: 6–12 months
Budget: $50k–100k one-time + $5k–10k/month Opex
Goals: Automation, centralization, enhanced security, scalability

## Slide 3: Current State Assessment
Hardware: 30 Lenovo desktops, unmanaged switches
Applications: VMware-hosted apps, custom exam browser
Workflow: Manual deployments, frequent reimaging
Network: No redundancy, no secure inter-site connectivity
Challenges: High overhead, outdated OS, scalability limits

## Slide 4: Risks in Current Setup
Single points of failure (on-prem backups)
Outdated OS (Windows 2016)
No centralized remote management
Geographic silos
High risk during exam periods

## Slide 5: Target Architecture (Hybrid → Cloud-Native)
Compute: AWS WorkSpaces/AppStream 2.0
Apps: Containerized browser (ECS/Fargate/Lambda)
Storage: S3 + Glacier, AWS Backup
Network: Global VPCs, VPN + Direct Connect, Global Accelerator
Management: CodeCommit, CodePipeline, Systems Manager
Security: IAM, GuardDuty, AWS Config, MFA
Monitoring: CloudWatch, X-Ray

## Slide 6: Phased Migration Plan
Phase 1 (Weeks 1–4): Assessment & Planning
Inventory assets, security audit, training
Migration roadmap + pilot
Phase 2 (Months 2–6): Migration & Implementation
Lift-and-shift VMs, upgrade OS
WorkSpaces, Directory Service
Refactor browser to PWA
VPN + Direct Connect rollout
Pilot in Brazil, then USA

## Slide 7: Phased Migration Plan (cont’d)
Phase 3 (Months 7–9): Optimization & Scaling
Cost optimization, ECS scaling
Systems Manager remote fixes
Expand to Japan, Italy, SE Asia
Phase 4 (Month 10+): Ongoing Ops
AWS Organizations for governance
DR: RPO <1h, RTO <4h
24/7 monitoring
Quarterly reviews + ML automation

## Slide 8: Risks & Mitigations
Downtime → Blue-green deployments
Data sovereignty → Regional S3 storage
Cost overruns → AWS Budgets
Skill gaps → Partner consultants, certifications
Security breaches → Pen testing, encryption

## Slide 9: Expected Benefits
Automation: 80% fewer manual tasks
Scalability: Growth to 10+ countries
Security: Redundant, encrypted network
Cost savings: 70% less reimaging costs
Global reach: Seamless connectivity across centers

## Slide 10: Next Steps
Approve migration roadmap
Schedule kickoff workshop
Launch AWS pilot in São Paulo HQ
Establish governance & reporting

## Slide 11: Closing
Positioning Balerica Inc. as a Modern, Cloud-First Education Provider
- Future-proofed
- Secure & compliant
- Scalable across 5+ countries
- Competitive edge